CAPA-2025-000503 | QMS Training Process Gap (ref. QMS Internal Audit Sonova and Unitron Canada FY2022/2023) | Completion Review | INWORKS | Leo Lau | Jennifer Penn | 2025-05-28 18:55 | 5200 | CAPA | 2026-05-28 | Training |  | tVerifyCAPACompletion |  | 2025-11-30 | 2025-11-28 23:00 | 2025-10-10 17:18
CAPA-2025-000503 | QMS Training Process Gap (ref. QMS Internal Audit Sonova and Unitron Canada FY2022/2023) | Completion Review | INWORKS | Leo Lau | Jennifer Penn | 2025-05-28 18:55 | 5200 | CAPA | 2026-05-28 | Training |  | tVerifyCAPACompletion |  | 2025-11-30 | 2025-11-28 23:00 | 2025-10-10 17:18
CAPA-2025-000506 | Incoming Inspection records discrepancy / SOCM 2025 External Audit Observation | Completion Review | INWORKS | Zehao Liang | Rosalva Aceves Gastelum | 2025-06-04 20:27 | 6255 | External Audit | 2026-06-04 | Document & Record Control |  | tVerifyCAPACompletion |  | 2025-10-10 10:20 |  | 2025-10-10 17:21
CAPA-2025-000506 | Incoming Inspection records discrepancy / SOCM 2025 External Audit Observation | Completion Review | INWORKS | Zehao Liang | Rosalva Aceves Gastelum | 2025-06-04 20:27 | 6255 | External Audit | 2026-06-04 | Document & Record Control |  | tVerifyCAPACompletion |  | 2025-12-31 | 2025-12-29 23:00 | 2025-10-10 17:21
CAPA-2025-000539 | Uptrend VA complaints of referenced orders not sent together | Investigation | INWORKS | Jorge Gomez | Zehao Liang | 2025-09-26 23:27 | 6255 | Customer Complaint Handling | 2025-11-10 | Product Service |  | tInvestigateCAPA |  | 2025-10-10 14:45 |  | 2025-10-10 21:46
CAPA-2025-000539 | Uptrend VA complaints of referenced orders not sent together | Investigation | INWORKS | Jorge Gomez | Zehao Liang | 2025-09-26 23:27 | 6255 | Customer Complaint Handling | 2025-11-10 | Product Service |  | tInvestigateCAPA |  | 2025-11-10 | 2025-11-08 23:00 | 2025-10-10 21:46
CAPA-2025-000507 | Incomplete traceability in production orders / SOCM 2025 external audit observation | Completion Review | INWORKS | Manuel Carballo Mendoza | Zehao Liang | 2025-06-04 20:40 | 6255 | External Audit | 2026-06-04 | Manufacturing |  | tVerifyImplementation | 2025-10-17 22:09 | 2025-10-10 15:09 |  | 2025-10-17 22:09
CAPA-2025-000507 | Incomplete traceability in production orders / SOCM 2025 external audit observation | Completion Review | INWORKS | Manuel Carballo Mendoza | Zehao Liang | 2025-06-04 20:40 | 6255 | External Audit | 2026-06-04 | Manufacturing |  | tVerifyImplementation | 2025-10-17 22:09 | 2025-10-10 15:09 |  | 2025-10-17 22:09
CAPA-2022-000187 | Computer System Validation (CSV) workflow is too complex, and is thus not well understood or consistently implemented | Closed | CLOSED | Fadime Hosoglu Leahy | Omid Jalili | 2022-03-10 21:24 | 1100 | Improvement Opportunities | 2026-04-07 | Quality- / Environment Management | 2025-10-13 06:18 |  |  |  |  | 2025-10-13 06:18
CAPA-2022-000187 | Computer System Validation (CSV) workflow is too complex, and is thus not well understood or consistently implemented | Closed | CLOSED | Fadime Hosoglu Leahy | Omid Jalili | 2022-03-10 21:24 | 1100 | Improvement Opportunities | 2026-04-07 | Quality- / Environment Management | 2025-10-13 06:18 |  |  |  |  | 2025-10-13 06:18
CAPA-2022-000187 | Computer System Validation (CSV) workflow is too complex, and is thus not well understood or consistently implemented | Closed | CLOSED | Fadime Hosoglu Leahy | Omid Jalili | 2022-03-10 21:24 | 1100 | Improvement Opportunities | 2026-04-07 | Quality- / Environment Management | 2025-10-13 06:18 |  |  |  |  | 2025-10-13 06:18
CAPA-2022-000187 | Computer System Validation (CSV) workflow is too complex, and is thus not well understood or consistently implemented | Closed | CLOSED | Fadime Hosoglu Leahy | Omid Jalili | 2022-03-10 21:24 | 1100 | Improvement Opportunities | 2026-04-07 | Quality- / Environment Management | 2025-10-13 06:18 |  |  |  |  | 2025-10-13 06:18
CAPA-2025-000526 | Missing Traceability Records for Key Component Identification | Investigation | INWORKS | Scott Alcock | Reanne Hamilton | 2025-07-15 16:05 | 2550 | External Audit | 2025-11-21 | Manufacturing |  | tApproveDueDateExtension | 2025-10-13 09:02 | 2025-10-13 09:02 |  | 2025-10-13 09:02
CAPA-2025-000526 | Missing Traceability Records for Key Component Identification | Investigation | INWORKS | Scott Alcock | Reanne Hamilton | 2025-07-15 16:05 | 2550 | External Audit | 2025-11-21 | Manufacturing |  | tApproveDueDateExtension | 2025-10-13 09:02 | 2025-10-13 09:02 |  | 2025-10-13 09:02
CAPA-2025-000525 | Incomplete Traceability of Production Activities | Investigation | INWORKS | Scott Alcock | Reanne Hamilton | 2025-07-15 16:02 | 2550 | External Audit | 2025-11-21 | Manufacturing |  | tApproveDueDateExtension | 2025-10-13 09:19 | 2025-10-13 09:18 |  | 2025-10-13 09:19
CAPA-2025-000525 | Incomplete Traceability of Production Activities | Investigation | INWORKS | Scott Alcock | Reanne Hamilton | 2025-07-15 16:02 | 2550 | External Audit | 2025-11-21 | Manufacturing |  | tApproveDueDateExtension | 2025-10-13 09:19 | 2025-10-13 09:18 |  | 2025-10-13 09:19
CAPA-2025-000542 | QMS Internal Audit Sonova Hearing SOCC FY2025/2026 | Investigation | INWORKS | Seaky Fan | Joy Zhou | 2025-10-10 05:51 | 7400 | Audit | 2025-11-24 | CAPA/NC |  | tInvestigateCAPA |  | 2025-10-15 15:33 |  | 2025-10-15 07:33
CAPA-2025-000542 | QMS Internal Audit Sonova Hearing SOCC FY2025/2026 | Investigation | INWORKS | Seaky Fan | Joy Zhou | 2025-10-10 05:51 | 7400 | Audit | 2025-11-24 | CAPA/NC |  | tInvestigateCAPA |  | 2025-11-24 | 2025-11-22 23:00 | 2025-10-15 07:33
CAPA-2025-000543 | QMS Internal Audit Sonova Hearing SOCC FY2025/2026 | Investigation | INWORKS | Seaky Fan | Joy Zhou | 2025-10-10 05:51 | 7400 | Audit | 2025-11-24 | Document & Record Control |  | tInvestigateCAPA |  | 2025-10-15 15:58 |  | 2025-10-15 07:58
CAPA-2025-000543 | QMS Internal Audit Sonova Hearing SOCC FY2025/2026 | Investigation | INWORKS | Seaky Fan | Joy Zhou | 2025-10-10 05:51 | 7400 | Audit | 2025-11-24 | Document & Record Control |  | tInvestigateCAPA |  | 2025-11-24 | 2025-11-22 23:00 | 2025-10-15 07:58
CAPA-2025-000544 | QMS Internal Audit Sonova Hearing SOCC FY2025/2026 | Investigation | INWORKS | Seaky Fan | Joy Zhou | 2025-10-10 05:51 | 7400 | Audit | 2025-11-24 | Manufacturing Engineering |  | tInvestigateCAPA |  | 2025-10-15 16:03 |  | 2025-10-21 00:26
CAPA-2025-000544 | QMS Internal Audit Sonova Hearing SOCC FY2025/2026 | Investigation | INWORKS | Seaky Fan | Joy Zhou | 2025-10-10 05:51 | 7400 | Audit | 2025-11-24 | Manufacturing Engineering |  | tInvestigateCAPA |  | 2025-11-24 | 2025-11-22 23:00 | 2025-10-21 00:26
CAPA-2025-000501 | Volume of clarifications | Implementation | INWORKS | Mark Critchley | Reanne Hamilton | 2025-05-19 09:38 | 2550 | Other | 2026-10-01 | Order Management & Return |  | tApproveCAPAInvestigation | 2025-10-17 14:12 | 2025-10-15 14:18 |  | 2025-10-17 14:12
CAPA-2025-000501 | Volume of clarifications | Implementation | INWORKS | Mark Critchley | Reanne Hamilton | 2025-05-19 09:38 | 2550 | Other | 2026-10-01 | Order Management & Return |  | tApproveCAPAInvestigation | 2025-10-17 14:12 | 2025-10-01 |  | 2025-10-17 14:12
CAPA-2025-000545 | QMS Internal Audit Sonova Hearing SOCC FY2025/2026 | Investigation | INWORKS | Seaky Fan | Seaky Fan | 2025-10-10 05:51 | 7400 | Audit | 2025-11-24 | Manufacturing Engineering |  | tInvestigateCAPA |  | 2025-10-16 08:57 |  | 2025-10-16 00:57
CAPA-2025-000545 | QMS Internal Audit Sonova Hearing SOCC FY2025/2026 | Investigation | INWORKS | Seaky Fan | Seaky Fan | 2025-10-10 05:51 | 7400 | Audit | 2025-11-24 | Manufacturing Engineering |  | tInvestigateCAPA |  | 2025-11-24 | 2025-11-22 23:00 | 2025-10-16 00:57
CAPA-2025-000546 | QMS Internal Audit Sonova Hearing SOCC FY2025/2026 | Investigation | INWORKS | Rick Xu | Seaky Fan | 2025-10-10 05:51 | 7400 | Audit | 2025-11-24 | Manufacturing |  | tInvestigateCAPA |  | 2025-10-16 09:21 |  | 2025-10-16 03:23
CAPA-2025-000546 | QMS Internal Audit Sonova Hearing SOCC FY2025/2026 | Investigation | INWORKS | Rick Xu | Seaky Fan | 2025-10-10 05:51 | 7400 | Audit | 2025-11-24 | Manufacturing |  | tInvestigateCAPA |  | 2025-11-24 | 2025-11-22 23:00 | 2025-10-16 03:23
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tApproveCAPAInvestigation | 2025-10-17 23:27 | 2025-10-16 11:40 |  | 2025-10-30 22:24
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tApproveCAPAInvestigation | 2025-10-17 13:49 | 2025-10-23 |  | 2025-10-17 23:27
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tApproveCAPAInvestigation | 2025-10-17 23:27 | 2025-10-23 |  | 2025-10-17 23:27
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tApproveCAPAInvestigation | 2025-10-17 23:27 | 2025-10-23 |  | 2025-10-17 23:27
CAPA-2025-000501 | Volume of clarifications | Implementation | INWORKS | Mark Critchley | Reanne Hamilton | 2025-05-19 09:38 | 2550 | Other | 2026-10-01 | Order Management & Return |  | tImplementActionPlans |  | 2025-10-17 14:12 |  | 2025-10-17 14:12
CAPA-2025-000501 | Volume of clarifications | Implementation | INWORKS | Mark Critchley | Reanne Hamilton | 2025-05-19 09:38 | 2550 | Other | 2026-10-01 | Order Management & Return |  | tImplementActionPlans |  | 2025-12-19 | 2025-12-17 23:00 | 2025-10-17 14:12
CAPA-2025-000501 | Volume of clarifications | Implementation | INWORKS | Mark Critchley | Reanne Hamilton | 2025-05-19 09:38 | 2550 | Other | 2026-10-01 | Order Management & Return |  | tImplementActionPlans |  | 2025-12-19 | 2025-12-17 23:00 | 2025-10-17 14:12
CAPA-2024-000472 | Specsavers Re-Charge File Discrepancies | Completion Review | INWORKS | Adam Sharples | Reanne Hamilton | 2024-11-27 15:24 | 2500 | NC | 2026-04-11 | Sales Inventory & Operation planning |  | tVerifyCAPACompletion |  | 2025-10-17 14:31 |  | 2025-10-21 18:12
CAPA-2024-000472 | Specsavers Re-Charge File Discrepancies | Completion Review | INWORKS | Adam Sharples | Reanne Hamilton | 2024-11-27 15:24 | 2500 | NC | 2026-04-11 | Sales Inventory & Operation planning |  | tVerifyCAPACompletion |  | 2025-06-30 |  | 2025-10-21 18:12
CAPA-2024-000453 | QMS Internal Audit Sonova do Brasil FY2023/2024 - Failure in the control and monitoring in the storage temperature conditions in Manufacturing area. | Investigation | INWORKS | Rafael Massola | Fernanda Meisel | 2024-08-26 15:12 | 6300 | Audit | 2024-11-25 | Facility Management |  | tVerifyImplementation | 2025-10-20 11:07 | 2025-10-17 15:09 |  | 2025-10-20 12:35
CAPA-2024-000453 | QMS Internal Audit Sonova do Brasil FY2023/2024 - Failure in the control and monitoring in the storage temperature conditions in Manufacturing area. | Investigation | INWORKS | Rafael Massola | Fernanda Meisel | 2024-08-26 15:12 | 6300 | Audit | 2024-11-25 | Facility Management |  | tVerifyImplementation | 2025-10-20 11:07 | 2025-10-17 15:09 |  | 2025-10-20 11:07
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tVerifyCAPAEffectiveness | 2025-10-17 19:42 | 2025-10-17 14:06 |  | 2025-10-22 23:31
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tVerifyCAPAEffectiveness | 2025-10-17 19:42 | 2026-04-15 | 2026-04-13 22:00 | 2025-10-17 19:42
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tCRBApproval | 2025-10-22 23:31 | 2025-10-17 15:42 |  | 2025-10-22 23:31
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tCRBApproval | 2025-10-22 23:31 | 2025-10-17 15:42 |  | 2025-10-22 23:31
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tCRBApproval | 2025-10-21 15:37 | 2025-10-17 15:42 |  | 2025-10-22 23:31
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tCRBApproval | 2025-10-17 20:31 | 2025-10-17 15:42 |  | 2025-10-22 23:31
CAPA-2025-000507 | Incomplete traceability in production orders / SOCM 2025 external audit observation | Completion Review | INWORKS | Manuel Carballo Mendoza | Zehao Liang | 2025-06-04 20:40 | 6255 | External Audit | 2026-06-04 | Manufacturing |  | tVerifyCAPACompletion |  | 2025-10-17 15:09 |  | 2025-10-17 22:09
CAPA-2025-000507 | Incomplete traceability in production orders / SOCM 2025 external audit observation | Completion Review | INWORKS | Manuel Carballo Mendoza | Zehao Liang | 2025-06-04 20:40 | 6255 | External Audit | 2026-06-04 | Manufacturing |  | tVerifyCAPACompletion |  | 2026-05-29 | 2026-05-27 22:00 | 2025-10-17 22:09
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tInvestigateCAPA | 2025-10-29 23:05 | 2025-10-17 16:27 |  | 2025-10-30 22:24
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tInvestigateCAPA | 2025-10-29 23:05 | 2025-10-23 |  | 2025-10-29 23:05
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-20 13:50 | 2025-10-20 13:05 |  | 2025-10-20 13:51
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-20 13:47 | 2025-11-19 |  | 2025-10-20 13:50
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-20 11:16 | 2025-11-19 |  | 2025-10-20 13:50
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-20 13:50 | 2025-11-19 |  | 2025-10-20 13:50
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-20 11:20 | 2025-11-19 |  | 2025-10-20 13:50
CAPA-2024-000453 | QMS Internal Audit Sonova do Brasil FY2023/2024 - Failure in the control and monitoring in the storage temperature conditions in Manufacturing area. | Investigation | INWORKS | Rafael Massola | Fernanda Meisel | 2024-08-26 15:12 | 6300 | Audit | 2024-11-25 | Facility Management |  | tInvestigateCAPA |  | 2025-10-20 08:07 |  | 2025-10-20 12:35
CAPA-2024-000453 | QMS Internal Audit Sonova do Brasil FY2023/2024 - Failure in the control and monitoring in the storage temperature conditions in Manufacturing area. | Investigation | INWORKS | Rafael Massola | Fernanda Meisel | 2024-08-26 15:12 | 6300 | Audit | 2024-11-25 | Facility Management |  | tInvestigateCAPA |  | 2024-11-25 |  | 2025-10-20 12:35
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tImplementActionPlans |  | 2025-10-20 15:50 |  | 2025-10-20 13:51
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tImplementActionPlans |  | 2026-03-31 | 2026-03-29 22:00 | 2025-10-20 13:51
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tImplementActionPlans |  | 2026-01-31 | 2026-01-29 23:00 | 2025-10-20 13:51
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tImplementActionPlans |  | 2026-02-28 | 2026-02-26 23:00 | 2025-10-20 13:51
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tImplementActionPlans |  | 2026-03-31 | 2026-03-29 22:00 | 2025-10-20 13:51
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tImplementActionPlans |  | 2026-03-31 | 2026-03-29 22:00 | 2025-10-20 13:51
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tImplementActionPlans |  | 2026-03-31 | 2026-03-29 22:00 | 2025-10-20 13:51
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tImplementActionPlans |  | 2026-01-31 | 2026-01-29 23:00 | 2025-10-20 13:51
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tImplementActionPlans |  | 2026-03-31 | 2026-03-29 22:00 | 2025-10-20 13:51
CAPA-2025-000524 | Incomplete Identification of Nonconforming Packaging in Quarantine Area | Investigation Approval | INWORKS | Loredana Neagu | Reanne Hamilton | 2025-07-15 15:58 | 2550 | External Audit | 2025-11-10 | CAPA/NC |  | tApproveCAPAInvestigation | 2025-10-27 11:51 | 2025-10-20 14:49 |  | 2025-10-30 12:16
CAPA-2025-000524 | Incomplete Identification of Nonconforming Packaging in Quarantine Area | Investigation Approval | INWORKS | Loredana Neagu | Reanne Hamilton | 2025-07-15 15:58 | 2550 | External Audit | 2025-11-10 | CAPA/NC |  | tApproveCAPAInvestigation | 2025-10-27 11:51 | 2025-11-10 |  | 2025-10-27 11:51
CAPA-2025-000540 | QMS Internal Audit Sonova/Unitron Canada FY2023/2024 - Training Management is not well-maintained | Investigation | INWORKS | Miroslaw Brelik | Chet Shah | 2025-10-08 18:36 | 5200 | Audit | 2025-11-22 | Quality- / Environment Management |  | tInvestigateCAPA |  | 2025-10-20 11:27 |  | 2025-10-20 15:28
CAPA-2025-000540 | QMS Internal Audit Sonova/Unitron Canada FY2023/2024 - Training Management is not well-maintained | Investigation | INWORKS | Miroslaw Brelik | Chet Shah | 2025-10-08 18:36 | 5200 | Audit | 2025-11-22 | Quality- / Environment Management |  | tInvestigateCAPA |  | 2025-11-22 | 2025-11-20 23:00 | 2025-10-20 15:28
CAPA-2025-000541 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Investigation | INWORKS | Naz Shew | Chet Shah | 2025-10-08 23:31 | 5200 | Audit | 2025-11-22 | Manufacturing |  | tInvestigateCAPA |  | 2025-10-20 11:35 |  | 2025-10-20 15:35
CAPA-2025-000541 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Investigation | INWORKS | Naz Shew | Chet Shah | 2025-10-08 23:31 | 5200 | Audit | 2025-11-22 | Manufacturing |  | tInvestigateCAPA |  | 2025-11-22 | 2025-11-20 23:00 | 2025-10-20 15:35
CAPA-2025-000547 | Overheated Adeo P devices while in use | Initiation Verification | INWORKS | Shokoufeh Khodabandeh | CAPACoordinator Stäfa | 2025-10-21 12:30 | 1100 | Other |  |  |  | tVerifyCAPAInitiation |  | 2025-10-21 14:30 |  | 2025-10-28 08:23
CAPA-2025-000547 | Overheated Adeo P devices while in use | Initiation Verification | INWORKS | Shokoufeh Khodabandeh | CAPACoordinator Stäfa | 2025-10-21 12:30 | 1100 | Other |  |  |  | tVerifyCAPAInitiation |  | 2025-10-21 14:30 |  | 2025-10-28 08:23
CAPA-2025-000486 | Incomplete documentation and records related to the qualifications of local suppliers | CRB Approval | INWORKS | Omveer Khanchi | Reanne Hamilton | 2025-01-24 16:42 | 2550 | External Audit | 2026-04-01 | Procurement & Supplier Control | 2025-09-29 13:44 | tCRBApproval |  | 2025-10-21 15:15 |  | 2025-10-21 15:15
CAPA-2025-000486 | Incomplete documentation and records related to the qualifications of local suppliers | CRB Approval | INWORKS | Omveer Khanchi | Reanne Hamilton | 2025-01-24 16:42 | 2550 | External Audit | 2026-04-01 | Procurement & Supplier Control | 2025-09-29 13:44 | tCRBApproval |  | 2025-10-21 15:15 |  | 2025-10-21 15:15
CAPA-2025-000486 | Incomplete documentation and records related to the qualifications of local suppliers | CRB Approval | INWORKS | Omveer Khanchi | Reanne Hamilton | 2025-01-24 16:42 | 2550 | External Audit | 2026-04-01 | Procurement & Supplier Control | 2025-09-29 13:44 | tCRBApproval |  | 2025-10-21 15:15 |  | 2025-10-21 15:15
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tApproveDueDateExtension | 2025-10-23 16:18 | 2025-10-22 13:44 |  | 2025-10-23 16:18
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tApproveDueDateExtension | 2025-10-23 16:18 | 2025-10-22 13:44 |  | 2025-10-23 16:18
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 |  |  |  |  | 2025-10-22 23:31
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 |  |  |  |  | 2025-10-22 23:31
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 |  |  |  |  | 2025-10-22 23:31
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 |  |  |  |  | 2025-10-22 23:31
CAPA-2022-000249 | Sonova USA - Internal Audit - NC 07 - No procedure containing statistical techniques is established | Completion Review | INWORKS | Aurèle Tenaud | Omid Jalili | 2022-12-15 19:27 | 1100 | Internal Audit | 2026-04-07 | Quality- / Environment Management |  | tApproveDueDateExtension | 2025-10-23 07:21 | 2025-10-23 09:13 |  | 2025-10-23 07:21
CAPA-2022-000249 | Sonova USA - Internal Audit - NC 07 - No procedure containing statistical techniques is established | Completion Review | INWORKS | Aurèle Tenaud | Omid Jalili | 2022-12-15 19:27 | 1100 | Internal Audit | 2026-04-07 | Quality- / Environment Management |  | tApproveDueDateExtension | 2025-10-23 07:21 | 2025-10-23 09:13 |  | 2025-10-23 07:21
CAPA-2025-000534 | Parts released without ISIR | Investigation | INWORKS | Diana Waldmann | Omid Jalili | 2025-09-09 07:36 | 1100 | NC | 2025-12-08 |  |  | tInvestigateCAPA |  | 2025-10-23 09:29 |  | 2025-10-23 07:34
CAPA-2025-000534 | Parts released without ISIR | Investigation | INWORKS | Diana Waldmann | Omid Jalili | 2025-09-09 07:36 | 1100 | NC | 2025-12-08 |  |  | tInvestigateCAPA |  | 2025-10-24 |  | 2025-10-23 07:34
CAPA-2025-000534 | Parts released without ISIR | Investigation | INWORKS | Diana Waldmann | Omid Jalili | 2025-09-09 07:36 | 1100 | NC | 2025-12-08 |  |  | tApproveDueDateExtension | 2025-10-23 07:34 | 2025-10-23 09:32 |  | 2025-10-23 07:34
CAPA-2025-000534 | Parts released without ISIR | Investigation | INWORKS | Diana Waldmann | Omid Jalili | 2025-09-09 07:36 | 1100 | NC | 2025-12-08 |  |  | tApproveDueDateExtension | 2025-10-23 07:34 | 2025-10-23 09:32 |  | 2025-10-23 07:34
CAPA-2025-000548 | ITE 60 Day Reliability Rate KPI in the Red for 3 Months | Initiation Verification | INWORKS | Reanne Hamilton | Reanne Hamilton | 2025-10-23 14:28 | 2550 | Other |  | Manufacturing |  | tVerifyCAPAInitiation |  | 2025-10-23 14:28 |  | 2025-10-23 14:29
CAPA-2025-000548 | ITE 60 Day Reliability Rate KPI in the Red for 3 Months | Initiation Verification | INWORKS | Reanne Hamilton | Reanne Hamilton | 2025-10-23 14:28 | 2550 | Other |  | Manufacturing |  | tVerifyCAPAInitiation |  | 2025-10-23 14:28 |  | 2025-10-23 14:29
CAPA-2025-000549 | Freight costs above budget April 2024 - February 2025 | Initiation Verification | INWORKS | Anna Rajtmajer | Reanne Hamilton | 2025-10-23 19:36 | 2550 | Management Review |  | Sales Inventory & Operation planning |  | tVerifyCAPAInitiation |  | 2025-10-23 19:36 |  | 2025-10-23 19:36
CAPA-2025-000549 | Freight costs above budget April 2024 - February 2025 | Initiation Verification | INWORKS | Anna Rajtmajer | Reanne Hamilton | 2025-10-23 19:36 | 2550 | Management Review |  | Sales Inventory & Operation planning |  | tVerifyCAPAInitiation |  | 2025-10-23 19:36 |  | 2025-10-23 19:36
CAPA-2025-000550 | Reduce RIC Detect HI Issues | Investigation | INWORKS | Claire Leishman | Reanne Hamilton | 2025-10-24 07:36 | 2550 | Improvement Opportunities | 2025-12-08 | Product Service |  | tVerifyCAPAInitiation | 2025-10-31 14:18 | 2025-10-24 07:36 |  | 2025-10-31 14:18
CAPA-2025-000550 | Reduce RIC Detect HI Issues | Investigation | INWORKS | Claire Leishman | Reanne Hamilton | 2025-10-24 07:36 | 2550 | Improvement Opportunities | 2025-12-08 | Product Service |  | tVerifyCAPAInitiation | 2025-10-31 14:18 | 2025-10-24 07:36 |  | 2025-10-31 14:18
CAPA-2023-000343 | Sonova Canada - GMED Audit - Controls for outsourced processes (Sonova Canada - 5200) | Completion Review | INWORKS | Shabeena Ibrahim | Omid Jalili | 2023-12-08 21:03 | 5200 | External Audit | 2026-03-31 | Quality- / Environment Management |  | tApproveDueDateExtension | 2025-10-25 08:47 | 2025-10-24 14:06 |  | 2025-10-25 08:47
CAPA-2023-000343 | Sonova Canada - GMED Audit - Controls for outsourced processes (Sonova Canada - 5200) | Completion Review | INWORKS | Shabeena Ibrahim | Omid Jalili | 2023-12-08 21:03 | 5200 | External Audit | 2026-03-31 | Quality- / Environment Management |  | tApproveDueDateExtension | 2025-10-25 08:47 | 2025-10-24 14:06 |  | 2025-10-25 08:47
CAPA-2025-000524 | Incomplete Identification of Nonconforming Packaging in Quarantine Area | Investigation Approval | INWORKS | Loredana Neagu | Reanne Hamilton | 2025-07-15 15:58 | 2550 | External Audit | 2025-11-10 | CAPA/NC |  | tInvestigateCAPA | 2025-10-30 12:16 | 2025-10-27 11:51 |  | 2025-10-30 12:16
CAPA-2025-000524 | Incomplete Identification of Nonconforming Packaging in Quarantine Area | Investigation Approval | INWORKS | Loredana Neagu | Reanne Hamilton | 2025-07-15 15:58 | 2550 | External Audit | 2025-11-10 | CAPA/NC |  | tInvestigateCAPA | 2025-10-30 12:16 | 2025-11-10 | 2025-11-08 23:00 | 2025-10-30 12:16
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs | 2025-10-28 11:41 | tVerifyCAPAEffectiveness | 2025-10-28 02:13 | 2025-10-27 14:31 |  | 2025-10-28 11:41
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs | 2025-10-28 11:41 | tVerifyCAPAEffectiveness | 2025-10-28 02:13 | 2026-04-25 | 2026-04-23 22:00 | 2025-10-28 02:13
CAPA-2025-000520 | QMS Internal Audit Sonova USA FY2023/2024 | Investigation Approval | INWORKS | Minal Maurya | Andres Uribe | 2025-06-30 21:22 | 5100 | Audit | 2025-11-12 | Quality- / Environment Management |  | tApproveCAPAInvestigation |  | 2025-10-27 15:58 |  | 2025-10-27 21:01
CAPA-2025-000520 | QMS Internal Audit Sonova USA FY2023/2024 | Investigation Approval | INWORKS | Minal Maurya | Andres Uribe | 2025-06-30 21:22 | 5100 | Audit | 2025-11-12 | Quality- / Environment Management |  | tApproveCAPAInvestigation |  | 2025-11-12 |  | 2025-10-27 21:01
CAPA-2025-000520 | QMS Internal Audit Sonova USA FY2023/2024 | Investigation Approval | INWORKS | Minal Maurya | Andres Uribe | 2025-06-30 21:22 | 5100 | Audit | 2025-11-12 | Quality- / Environment Management |  | tApproveCAPAInvestigation |  | 2025-11-12 |  | 2025-10-27 21:01
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs | 2025-10-28 11:41 | tCRBApproval | 2025-10-28 11:41 | 2025-10-27 22:13 |  | 2025-10-28 11:41
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs | 2025-10-28 11:41 | tCRBApproval | 2025-10-28 11:41 | 2025-10-27 22:13 |  | 2025-10-28 11:41
CAPA-2021-000096 | Custom products lacquered with Fotoplast lacquer 3 - Cytotoxicity test failed | Implementation Verification | INWORKS | Michael Takacs | Omid Jalili | 2021-01-21 08:44 | 1100 | Non Conformance | 2022-12-07 |  |  | tVerifyImplementation |  | 2025-10-28 11:44 |  | 2025-10-28 10:44
CAPA-2021-000096 | Custom products lacquered with Fotoplast lacquer 3 - Cytotoxicity test failed | Implementation Verification | INWORKS | Michael Takacs | Omid Jalili | 2021-01-21 08:44 | 1100 | Non Conformance | 2022-12-07 |  |  | tVerifyImplementation |  | 2025-10-28 11:44 |  | 2025-10-28 10:44
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs | 2025-10-28 11:41 |  |  |  |  | 2025-10-28 11:41
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs | 2025-10-28 11:41 |  |  |  |  | 2025-10-28 11:41
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs | 2025-10-28 11:41 |  |  |  |  | 2025-10-28 11:41
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs | 2025-10-28 11:41 |  |  |  |  | 2025-10-28 11:41
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tVerifyCAPAInitiation | 2025-10-29 23:11 | 2025-10-29 16:05 |  | 2025-10-30 22:24
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tVerifyCAPAInitiation | 2025-10-29 23:11 | 2025-10-29 16:05 |  | 2025-10-29 23:11
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tInvestigateCAPA | 2025-10-30 00:23 | 2025-10-29 16:11 |  | 2025-10-30 22:24
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tInvestigateCAPA | 2025-10-30 00:23 | 2025-12-05 | 2025-12-03 23:00 | 2025-10-30 00:23
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tApproveCAPAInvestigation |  | 2025-10-29 17:23 |  | 2025-10-30 22:24
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tApproveCAPAInvestigation | 2025-10-30 22:24 | 2025-12-05 |  | 2025-10-30 22:24
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tApproveCAPAInvestigation |  | 2025-12-05 |  | 2025-10-30 22:24
CAPA-2025-000533 | Recurrence of SAP routing not updated previously CAPA-2025-000469 closed as effective | Investigation Approval | INWORKS | Zehao Liang | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tApproveCAPAInvestigation |  | 2025-12-05 |  | 2025-10-30 22:24
CAPA-2025-000524 | Incomplete Identification of Nonconforming Packaging in Quarantine Area | Investigation Approval | INWORKS | Loredana Neagu | Reanne Hamilton | 2025-07-15 15:58 | 2550 | External Audit | 2025-11-10 | CAPA/NC |  | tApproveCAPAInvestigation |  | 2025-10-30 12:16 |  | 2025-10-30 12:16
CAPA-2025-000524 | Incomplete Identification of Nonconforming Packaging in Quarantine Area | Investigation Approval | INWORKS | Loredana Neagu | Reanne Hamilton | 2025-07-15 15:58 | 2550 | External Audit | 2025-11-10 | CAPA/NC |  | tApproveCAPAInvestigation |  | 2025-11-10 |  | 2025-10-30 12:16
CAPA-2025-000508 | AUD-EXT-2025-56 - GMED external audit (NC02) | Implementation Verification | INWORKS | Miroslaw Brelik | Leo Lau | 2025-06-06 14:44 | 5200 | External Audit | 2026-06-06 | Manufacturing Engineering |  | tVerifyImplementation | 2025-10-30 14:01 | 2025-10-30 08:36 |  | 2025-10-30 14:26
CAPA-2025-000508 | AUD-EXT-2025-56 - GMED external audit (NC02) | Implementation Verification | INWORKS | Miroslaw Brelik | Leo Lau | 2025-06-06 14:44 | 5200 | External Audit | 2026-06-06 | Manufacturing Engineering |  | tVerifyImplementation | 2025-10-30 14:01 | 2025-10-30 08:36 |  | 2025-10-30 14:01
CAPA-2025-000508 | AUD-EXT-2025-56 - GMED external audit (NC02) | Implementation Verification | INWORKS | Miroslaw Brelik | Leo Lau | 2025-06-06 14:44 | 5200 | External Audit | 2026-06-06 | Manufacturing Engineering |  | tVerifyCAPACompletion | 2025-10-30 14:25 | 2025-10-30 10:01 |  | 2025-10-30 14:26
CAPA-2025-000508 | AUD-EXT-2025-56 - GMED external audit (NC02) | Implementation Verification | INWORKS | Miroslaw Brelik | Leo Lau | 2025-06-06 14:44 | 5200 | External Audit | 2026-06-06 | Manufacturing Engineering |  | tVerifyCAPACompletion | 2025-10-30 14:25 | 2026-03-31 | 2026-03-29 22:00 | 2025-10-30 14:25
CAPA-2025-000508 | AUD-EXT-2025-56 - GMED external audit (NC02) | Implementation Verification | INWORKS | Miroslaw Brelik | Leo Lau | 2025-06-06 14:44 | 5200 | External Audit | 2026-06-06 | Manufacturing Engineering |  | tVerifyCAPACompletion | 2025-10-30 14:25 | 2026-03-31 | 2026-03-29 22:00 | 2025-10-30 14:25
CAPA-2025-000508 | AUD-EXT-2025-56 - GMED external audit (NC02) | Implementation Verification | INWORKS | Miroslaw Brelik | Leo Lau | 2025-06-06 14:44 | 5200 | External Audit | 2026-06-06 | Manufacturing Engineering |  | tVerifyImplementation |  | 2025-10-30 10:25 |  | 2025-10-30 14:26
CAPA-2025-000508 | AUD-EXT-2025-56 - GMED external audit (NC02) | Implementation Verification | INWORKS | Miroslaw Brelik | Leo Lau | 2025-06-06 14:44 | 5200 | External Audit | 2026-06-06 | Manufacturing Engineering |  | tVerifyImplementation |  | 2025-10-30 10:25 |  | 2025-10-30 14:26
CAPA-2024-000446 | Health Canada Inspection (2024) - [Observation #4] | Completion Review | INWORKS | Leo Lau | Omid Jalili | 2024-08-07 14:07 | 5200 | External Audit | 2025-12-19 | Regulatory Affairs |  | tVerifyImplementation | 2025-10-30 17:55 | 2025-10-30 13:55 |  | 2025-10-30 17:56
CAPA-2024-000446 | Health Canada Inspection (2024) - [Observation #4] | Completion Review | INWORKS | Leo Lau | Omid Jalili | 2024-08-07 14:07 | 5200 | External Audit | 2025-12-19 | Regulatory Affairs |  | tVerifyImplementation | 2025-10-30 17:55 | 2025-10-30 13:55 |  | 2025-10-30 17:56
CAPA-2024-000446 | Health Canada Inspection (2024) - [Observation #4] | Completion Review | INWORKS | Leo Lau | Omid Jalili | 2024-08-07 14:07 | 5200 | External Audit | 2025-12-19 | Regulatory Affairs |  | tVerifyCAPACompletion |  | 2025-10-30 13:55 |  | 2025-10-30 17:56
CAPA-2024-000446 | Health Canada Inspection (2024) - [Observation #4] | Completion Review | INWORKS | Leo Lau | Omid Jalili | 2024-08-07 14:07 | 5200 | External Audit | 2025-12-19 | Regulatory Affairs |  | tVerifyCAPACompletion |  | 2026-01-31 | 2026-01-29 23:00 | 2025-10-30 17:56
CAPA-2024-000429 | AUD-EXT-2024-33 -GMED external audit (NC03) | CRB Approval | INWORKS | Miroslaw Brelik | Leo Lau | 2024-07-05 01:49 | 5200 | External Audit | 2026-04-28 | Manufacturing |  | tVerifyCAPAEffectiveness | 2025-10-30 18:33 | 2025-10-30 14:22 |  | 2025-10-30 19:01
CAPA-2024-000429 | AUD-EXT-2024-33 -GMED external audit (NC03) | CRB Approval | INWORKS | Miroslaw Brelik | Leo Lau | 2024-07-05 01:49 | 5200 | External Audit | 2026-04-28 | Manufacturing |  | tVerifyCAPAEffectiveness | 2025-10-30 18:33 | 2026-04-28 | 2026-04-26 22:00 | 2025-10-30 18:33
CAPA-2024-000429 | AUD-EXT-2024-33 -GMED external audit (NC03) | CRB Approval | INWORKS | Miroslaw Brelik | Leo Lau | 2024-07-05 01:49 | 5200 | External Audit | 2026-04-28 | Manufacturing |  | tCRBApproval |  | 2025-10-30 14:33 |  | 2025-10-30 19:01
CAPA-2024-000429 | AUD-EXT-2024-33 -GMED external audit (NC03) | CRB Approval | INWORKS | Miroslaw Brelik | Leo Lau | 2024-07-05 01:49 | 5200 | External Audit | 2026-04-28 | Manufacturing |  | tCRBApproval | 2025-10-30 19:01 | 2025-10-30 14:33 |  | 2025-10-30 19:01
CAPA-2024-000429 | AUD-EXT-2024-33 -GMED external audit (NC03) | CRB Approval | INWORKS | Miroslaw Brelik | Leo Lau | 2024-07-05 01:49 | 5200 | External Audit | 2026-04-28 | Manufacturing |  | tCRBApproval |  | 2025-10-30 14:33 |  | 2025-10-30 19:01
CAPA-2025-000550 | Reduce RIC Detect HI Issues | Investigation | INWORKS | Claire Leishman | Reanne Hamilton | 2025-10-24 07:36 | 2550 | Improvement Opportunities | 2025-12-08 | Product Service |  | tInvestigateCAPA |  | 2025-10-31 14:18 |  | 2025-10-31 14:18
CAPA-2025-000550 | Reduce RIC Detect HI Issues | Investigation | INWORKS | Claire Leishman | Reanne Hamilton | 2025-10-24 07:36 | 2550 | Improvement Opportunities | 2025-12-08 | Product Service |  | tInvestigateCAPA |  | 2025-12-08 | 2025-12-06 23:00 | 2025-10-31 14:18
CAPA-2024-000430 | AUD-EXT-2024-33 - GMED external audit (NC05) | CRB Approval | INWORKS | Miroslaw Brelik | Leo Lau | 2024-07-05 01:58 | 5200 | External Audit | 2026-04-29 | Environmental Management |  | tCRBApproval |  | 2025-11-02 21:01 |  | 2025-11-03 02:02
CAPA-2024-000430 | AUD-EXT-2024-33 - GMED external audit (NC05) | CRB Approval | INWORKS | Miroslaw Brelik | Leo Lau | 2024-07-05 01:58 | 5200 | External Audit | 2026-04-29 | Environmental Management |  | tVerifyCAPAEffectiveness | 2025-11-03 02:01 | 2025-10-31 13:00 |  | 2025-11-03 02:02
CAPA-2024-000430 | AUD-EXT-2024-33 - GMED external audit (NC05) | CRB Approval | INWORKS | Miroslaw Brelik | Leo Lau | 2024-07-05 01:58 | 5200 | External Audit | 2026-04-29 | Environmental Management |  | tVerifyCAPAEffectiveness | 2025-11-03 02:01 | 2026-04-29 | 2026-04-27 22:00 | 2025-11-03 02:01
CAPA-2024-000430 | AUD-EXT-2024-33 - GMED external audit (NC05) | CRB Approval | INWORKS | Miroslaw Brelik | Leo Lau | 2024-07-05 01:58 | 5200 | External Audit | 2026-04-29 | Environmental Management |  | tCRBApproval |  | 2025-11-02 21:01 |  | 2025-11-03 02:02
CAPA-2025-000537 | Releasing uncontrol changes from the kaizen of parylene coating process | Investigation | INWORKS | Nhat Duy Luong | Vinh Thanh Ho | 2025-09-19 07:57 | 8400 | NC | 2025-11-03 | Document & Record Control |  | tInvestigateCAPA |  | 2025-11-03 16:21 |  | 2025-11-03 07:22
CAPA-2025-000537 | Releasing uncontrol changes from the kaizen of parylene coating process | Investigation | INWORKS | Nhat Duy Luong | Vinh Thanh Ho | 2025-09-19 07:57 | 8400 | NC | 2025-11-03 | Document & Record Control |  | tInvestigateCAPA |  | 2025-11-03 |  | 2025-11-03 07:22
CAPA-2025-000537 | Releasing uncontrol changes from the kaizen of parylene coating process | Investigation | INWORKS | Nhat Duy Luong | Vinh Thanh Ho | 2025-09-19 07:57 | 8400 | NC | 2025-11-03 | Document & Record Control |  | tApproveCAPAInvestigation | 2025-11-03 07:21 | 2025-10-31 13:15 |  | 2025-11-03 07:22
CAPA-2025-000537 | Releasing uncontrol changes from the kaizen of parylene coating process | Investigation | INWORKS | Nhat Duy Luong | Vinh Thanh Ho | 2025-09-19 07:57 | 8400 | NC | 2025-11-03 | Document & Record Control |  | tApproveCAPAInvestigation | 2025-11-03 07:21 | 2025-11-03 |  | 2025-11-03 07:21
CAPA-2025-000537 | Releasing uncontrol changes from the kaizen of parylene coating process | Investigation | INWORKS | Nhat Duy Luong | Vinh Thanh Ho | 2025-09-19 07:57 | 8400 | NC | 2025-11-03 | Document & Record Control |  | tApproveCAPAInvestigation | 2025-11-03 07:21 | 2025-11-03 |  | 2025-11-03 07:21
Total number of records: 12598

## Committed Date
CAPA Number | Committed Date | To be overdue
CAPA-2023-000275 | 2025-10-31 | On Time
CAPA-2023-000346 | 2025-11-30 | To be overdue
CAPA-2023-000312 | 31-Apr-26 | To be overdue
CAPA-2021-000096 | 2025-10-31 | To be overdue