CAPA-2025-000506 | Incoming Inspection records discrepancy / SOCM 2025 External Audit Observation | Completion Review | INWORKS | Zehao Liang | Rosalva Aceves Gastelum | 2025-06-04 20:27 | 6255 | External Audit | 2026-06-04 | Document & Record Control |  | tVerifyImplementation | 2025-10-10 17:20 | 2025-10-07 11:18 |  | 2025-10-10 17:21
CAPA-2025-000507 | Incomplete traceability in production orders / SOCM 2025 external audit observation | Completion Review | INWORKS | Manuel Carballo Mendoza | Zehao Liang | 2025-06-04 20:40 | 6255 | External Audit | 2026-06-04 | Manufacturing |  | tImplementActionPlans | 2025-10-10 13:45 | 2025-12-31 | 2025-12-29 23:00 | 2025-10-10 22:09
CAPA-2025-000507 | Incomplete traceability in production orders / SOCM 2025 external audit observation | Completion Review | INWORKS | Manuel Carballo Mendoza | Zehao Liang | 2025-06-04 20:40 | 6255 | External Audit | 2026-06-04 | Manufacturing |  | tImplementActionPlans | 2025-10-10 22:09 | 2026-02-27 | 2026-02-25 23:00 | 2025-10-10 22:09
CAPA-2025-000507 | Incomplete traceability in production orders / SOCM 2025 external audit observation | Completion Review | INWORKS | Manuel Carballo Mendoza | Zehao Liang | 2025-06-04 20:40 | 6255 | External Audit | 2026-06-04 | Manufacturing |  | tImplementActionPlans | 2025-10-07 18:58 | 2025-12-31 | 2025-12-29 23:00 | 2025-10-10 22:09
CAPA-2023-000343 | Sonova Canada - GMED Audit - Controls for outsourced processes (Sonova Canada - 5200) | Completion Review | INWORKS | Shabeena Ibrahim | Omid Jalili | 2023-12-08 21:03 | 5200 | External Audit | 2026-03-31 | Quality- / Environment Management |  | tApproveDueDateExtension | 2025-10-25 08:47 | 2025-10-24 14:06 |  | 2025-10-25 08:47
CAPA-2023-000343 | Sonova Canada - GMED Audit - Controls for outsourced processes (Sonova Canada - 5200) | Completion Review | INWORKS | Shabeena Ibrahim | Omid Jalili | 2023-12-08 21:03 | 5200 | External Audit | 2026-03-31 | Quality- / Environment Management |  | tApproveDueDateExtension | 2025-10-25 08:47 | 2025-10-24 14:06 |  | 2025-10-25 08:47
CAPA-2025-000533 | Not sustaining CAPA actions | Investigation | INWORKS | Saul Ruiz Vivanco | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tApproveCAPAInvestigation | 2025-10-17 23:27 | 2025-10-16 11:40 |  | 2025-10-23 16:18
CAPA-2025-000533 | Not sustaining CAPA actions | Investigation | INWORKS | Saul Ruiz Vivanco | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tApproveCAPAInvestigation | 2025-10-17 13:49 | 2025-10-23 |  | 2025-10-17 23:27
CAPA-2025-000501 | Volume of clarifications | Implementation | INWORKS | Mark Critchley | Reanne Hamilton | 2025-05-19 09:38 | 2550 | Other | 2026-10-01 | Order Management & Return |  | tImplementActionPlans |  | 2025-10-17 14:12 |  | 2025-10-17 14:12
CAPA-2025-000501 | Volume of clarifications | Implementation | INWORKS | Mark Critchley | Reanne Hamilton | 2025-05-19 09:38 | 2550 | Other | 2026-10-01 | Order Management & Return |  | tApproveCAPAInvestigation | 2025-10-17 14:12 | 2025-10-15 14:18 |  | 2025-10-17 14:12
CAPA-2025-000532 | Wrong BOM variant is active for 050-1048-P667 | Investigation Approval | INWORKS | Dina Koch | Rachel Longwell | 2025-08-15 10:32 | 1100 | NC | 2025-11-13 |  |  | tApproveCAPAInvestigation |  | 2025-10-10 17:17 |  | 2025-10-22 06:17
CAPA-2025-000532 | Wrong BOM variant is active for 050-1048-P667 | Investigation Approval | INWORKS | Dina Koch | Rachel Longwell | 2025-08-15 10:32 | 1100 | NC | 2025-11-13 |  |  | tApproveCAPAInvestigation | 2025-10-17 14:12 | 2025-11-13 |  | 2025-10-22 06:17
CAPA-2025-000532 | Wrong BOM variant is active for 050-1048-P667 | Investigation Approval | INWORKS | Dina Koch | Rachel Longwell | 2025-08-15 10:32 | 1100 | NC | 2025-11-13 |  |  | tApproveCAPAInvestigation | 2025-10-22 06:17 | 2025-11-13 |  | 2025-10-22 06:17
CAPA-2024-000472 | Specsavers Re-Charge File Discrepancies | Completion Review | INWORKS | Adam Sharples | Reanne Hamilton | 2024-11-27 15:24 | 2500 | NC | 2026-04-11 | Sales Inventory & Operation planning |  | tVerifyCAPACompletion |  | 2025-10-17 14:31 |  | 2025-10-21 18:12
CAPA-2024-000472 | Specsavers Re-Charge File Discrepancies | Completion Review | INWORKS | Adam Sharples | Reanne Hamilton | 2024-11-27 15:24 | 2500 | NC | 2026-04-11 | Sales Inventory & Operation planning |  | tVerifyCAPACompletion |  | 2025-06-30 |  | 2025-10-21 18:12
CAPA-2022-000249 | Sonova USA - Internal Audit - NC 07 - No procedure containing statistical techniques is established | Completion Review | INWORKS | Aurèle Tenaud | Omid Jalili | 2022-12-15 19:27 | 1100 | Internal Audit | 2026-04-07 | Quality- / Environment Management |  | tApproveDueDateExtension | 2025-10-23 07:21 | 2025-10-23 09:13 |  | 2025-10-23 07:21
CAPA-2022-000249 | Sonova USA - Internal Audit - NC 07 - No procedure containing statistical techniques is established | Completion Review | INWORKS | Aurèle Tenaud | Omid Jalili | 2022-12-15 19:27 | 1100 | Internal Audit | 2026-04-07 | Quality- / Environment Management |  | tApproveDueDateExtension | 2025-10-23 07:21 | 2025-10-23 09:13 |  | 2025-10-23 07:21
CAPA-2025-000534 | Parts released without ISIR | Investigation | INWORKS | Diana Waldmann | Omid Jalili | 2025-09-09 07:36 | 1100 | NC | 2025-12-08 |  |  | tInvestigateCAPA |  | 2025-10-23 09:29 |  | 2025-10-23 07:34
CAPA-2025-000534 | Parts released without ISIR | Investigation | INWORKS | Diana Waldmann | Omid Jalili | 2025-09-09 07:36 | 1100 | NC | 2025-12-08 |  |  | tInvestigateCAPA |  | 2025-10-24 |  | 2025-10-23 07:34
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-08 08:55 | 2025-10-06 11:50 |  | 2025-10-20 13:51
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-06 11:13 | 2025-11-19 |  | 2025-10-08 08:55
CAPA-2023-000312 | Lack of Incoming Inspection on Externally Sourced Components distributed by ARVATO | Implementation | INWORKS | Omid Jalili | Aurèle Tenaud | 2023-07-24 11:56 | 1100 | Other | 2025-10-21 | Procurement |  | tImplementActionPlans | 2024-12-19 14:26 | 2024-07-18 09:47 |  | 2025-10-21 22:00
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-06 11:01 | 2025-11-19 |  | 2025-10-08 08:55
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-06 11:27 | 2025-11-19 |  | 2025-10-08 08:55
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-08 08:55 | 2025-11-19 |  | 2025-10-08 08:55
CAPA-2023-000345 | Sonova Canada - GMED Audit - Establishing criteria for the selection of suppliers | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2023-12-08 21:08 | 5200 | External Audit | 2026-03-31 | Procurement | 2025-10-06 16:00 |  |  |  |  | 2025-10-06 16:00
CAPA-2023-000345 | Sonova Canada - GMED Audit - Establishing criteria for the selection of suppliers | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2023-12-08 21:08 | 5200 | External Audit | 2026-03-31 | Procurement | 2025-10-06 16:00 |  |  |  |  | 2025-10-06 16:00
CAPA-2023-000345 | Sonova Canada - GMED Audit - Establishing criteria for the selection of suppliers | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2023-12-08 21:08 | 5200 | External Audit | 2026-03-31 | Procurement | 2025-10-06 16:00 |  |  |  |  | 2025-10-06 16:00
CAPA-2023-000345 | Sonova Canada - GMED Audit - Establishing criteria for the selection of suppliers | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2023-12-08 21:08 | 5200 | External Audit | 2026-03-31 | Procurement | 2025-10-06 16:00 |  |  |  |  | 2025-10-06 16:00
CAPA-2025-000486 | Incomplete documentation and records related to the qualifications of local suppliers | CRB Approval | INWORKS | Omveer Khanchi | Reanne Hamilton | 2025-01-24 16:42 | 2550 | External Audit | 2026-04-01 | Procurement & Supplier Control | 2025-09-29 13:44 | tVerifyCAPAEffectiveness | 2025-10-21 15:15 | 2025-10-03 11:13 |  | 2025-10-21 15:15
CAPA-2025-000486 | Incomplete documentation and records related to the qualifications of local suppliers | CRB Approval | INWORKS | Omveer Khanchi | Reanne Hamilton | 2025-01-24 16:42 | 2550 | External Audit | 2026-04-01 | Procurement & Supplier Control | 2025-09-29 13:44 | tVerifyCAPAEffectiveness | 2025-10-21 15:15 | 2026-04-01 | 2026-03-30 22:00 | 2025-10-21 15:15
CAPA-2023-000345 | Sonova Canada - GMED Audit - Establishing criteria for the selection of suppliers | Closed | CLOSED | Shabeena Ibrahim | Leo Lau | 2023-12-08 21:08 | 5200 | External Audit | 2026-03-31 | Procurement | 2025-10-06 16:00 | tVerifyCAPAEffectiveness | 2025-10-03 11:26 | 2025-10-03 07:22 |  | 2025-10-06 16:00
CAPA-2025-000532 | Wrong BOM variant is active for 050-1048-P667 | Investigation Approval | INWORKS | Dina Koch | Rachel Longwell | 2025-08-15 10:32 | 1100 | NC | 2025-11-13 |  |  | tApproveCAPAInvestigation | 2025-10-07 13:11 | 2025-10-03 09:45 |  | 2025-10-22 06:17
CAPA-2025-000532 | Wrong BOM variant is active for 050-1048-P667 | Investigation Approval | INWORKS | Dina Koch | Rachel Longwell | 2025-08-15 10:32 | 1100 | NC | 2025-11-13 |  |  | tApproveCAPAInvestigation | 2025-10-07 13:11 | 2025-11-13 |  | 2025-10-07 13:11
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tInvestigateCAPA | 2025-10-06 09:50 | 2025-08-21 | 2025-11-17 23:00 | 2025-10-06 09:50
CAPA-2025-000498 | Sonova/Phonak AG - GMED Audit 2025 NC02 - The last management review planned and carried out in 2025 does not take into consideration customer satisfaction. | Completion Review | INWORKS | Aurèle Tenaud | Omid Jalili | 2025-03-24 08:16 | 1100 | External Audit | 2026-03-24 | Management Responsibilities |  | tVerifyImplementation | 2025-10-06 06:04 | 2025-10-03 10:59 |  | 2025-10-06 06:06
CAPA-2025-000498 | Sonova/Phonak AG - GMED Audit 2025 NC02 - The last management review planned and carried out in 2025 does not take into consideration customer satisfaction. | Completion Review | INWORKS | Aurèle Tenaud | Omid Jalili | 2025-03-24 08:16 | 1100 | External Audit | 2026-03-24 | Management Responsibilities |  | tVerifyImplementation | 2025-10-06 06:04 | 2025-10-03 10:59 |  | 2025-10-06 06:04
CAPA-2024-000417 | Supplier criticality and performance improvement | Implementation | INWORKS | Gino Stuewert | Diana Waldmann | 2024-07-01 11:52 | 1100 | CAPA | 2025-11-13 | Procurement |  | tVerifyCAPAInitiation | 2025-09-25 12:35 | 2025-09-25 14:21 |  | 2025-09-26 12:28
CAPA-2024-000417 | Supplier criticality and performance improvement | Implementation | INWORKS | Gino Stuewert | Diana Waldmann | 2024-07-01 11:52 | 1100 | CAPA | 2025-11-13 | Procurement |  | tVerifyCAPAInitiation | 2025-09-25 12:35 | 2025-09-25 14:21 |  | 2025-09-25 12:35
CAPA-2024-000453 | QMS Internal Audit Sonova do Brasil FY2023/2024 - Failure in the control and monitoring in the storage temperature conditions in Manufacturing area. | Investigation | INWORKS | Rafael Massola | Fernanda Meisel | 2024-08-26 15:12 | 6300 | Audit | 2024-11-25 | Facility Management |  | tVerifyImplementation | 2025-10-20 11:07 | 2025-10-17 15:09 |  | 2025-10-20 11:07
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tVerifyCAPAEffectiveness | 2025-10-17 19:42 | 2025-10-17 14:06 |  | 2025-10-22 23:31
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tVerifyCAPACompletion | 2025-10-17 19:06 | 2025-07-31 |  | 2025-10-17 19:06
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tApproveDueDateExtension | 2025-06-12 07:04 | 2025-06-11 11:38 |  | 2025-06-12 07:04
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tApproveDueDateExtension | 2025-06-12 07:04 | 2025-06-11 11:38 |  | 2025-06-12 07:04
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tCRBApproval | 2025-10-21 15:37 | 2025-10-17 15:42 |  | 2025-10-22 23:31
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tCRBApproval | 2025-10-17 20:31 | 2025-10-17 15:42 |  | 2025-10-22 23:31
CAPA-2025-000507 | Incomplete traceability in production orders / SOCM 2025 external audit observation | Completion Review | INWORKS | Manuel Carballo Mendoza | Zehao Liang | 2025-06-04 20:40 | 6255 | External Audit | 2026-06-04 | Manufacturing |  | tVerifyImplementation | 2025-10-17 22:09 | 2025-10-10 15:09 |  | 2025-10-17 22:09
CAPA-2025-000507 | Incomplete traceability in production orders / SOCM 2025 external audit observation | Completion Review | INWORKS | Manuel Carballo Mendoza | Zehao Liang | 2025-06-04 20:40 | 6255 | External Audit | 2026-06-04 | Manufacturing |  | tVerifyImplementation | 2025-10-17 22:09 | 2025-10-10 15:09 |  | 2025-10-17 22:09
CAPA-2025-000550 | RIC Detect HI | Initiation Verification | INWORKS | Anna Rajtmajer | Reanne Hamilton | 2025-10-24 07:36 | 2550 | Management Review |  | Product Service |  | tVerifyCAPAInitiation |  | 2025-10-24 07:36 |  | 2025-10-24 07:37
CAPA-2025-000550 | RIC Detect HI | Initiation Verification | INWORKS | Anna Rajtmajer | Reanne Hamilton | 2025-10-24 07:36 | 2550 | Management Review |  | Product Service |  | tVerifyCAPAInitiation |  | 2025-10-24 07:36 |  | 2025-10-24 07:37
CAPA-2025-000507 | Incomplete traceability in production orders / SOCM 2025 external audit observation | Completion Review | INWORKS | Manuel Carballo Mendoza | Zehao Liang | 2025-06-04 20:40 | 6255 | External Audit | 2026-06-04 | Manufacturing |  | tVerifyCAPACompletion |  | 2025-10-17 15:09 |  | 2025-10-17 22:09
CAPA-2025-000507 | Incomplete traceability in production orders / SOCM 2025 external audit observation | Completion Review | INWORKS | Manuel Carballo Mendoza | Zehao Liang | 2025-06-04 20:40 | 6255 | External Audit | 2026-06-04 | Manufacturing |  | tVerifyCAPACompletion |  | 2026-05-29 | 2026-05-27 22:00 | 2025-10-17 22:09
CAPA-2025-000533 | Not sustaining CAPA actions | Investigation | INWORKS | Saul Ruiz Vivanco | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tInvestigateCAPA |  | 2025-10-17 16:27 |  | 2025-10-23 16:18
CAPA-2025-000533 | Not sustaining CAPA actions | Investigation | INWORKS | Saul Ruiz Vivanco | Zehao Liang | 2025-09-09 00:27 | 6255 | CAPA | 2025-12-05 | Manufacturing Engineering |  | tInvestigateCAPA |  | 2025-10-23 |  | 2025-10-23 16:18
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tVerifyCAPAEffectiveness | 2025-10-17 19:42 | 2026-04-15 | 2026-04-13 22:00 | 2025-10-17 19:42
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tCRBApproval | 2025-10-22 23:31 | 2025-10-17 15:42 |  | 2025-10-22 23:31
CAPA-2023-000287 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | Closed | CLOSED | Leo Lau | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-15 | Quality- / Environment Management | 2025-10-22 23:31 | tCRBApproval | 2025-10-22 23:31 | 2025-10-17 15:42 |  | 2025-10-22 23:31
CAPA-2023-000285 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | CRB Approval | CLOSED | Naz Shew | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-05 | Manufacturing | 2025-10-08 23:31 | tVerifyCAPACompletion | 2025-10-07 15:09 | 2025-10-31 | 2025-10-29 23:00 | 2025-10-07 15:10
CAPA-2023-000285 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | CRB Approval | CLOSED | Naz Shew | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-05 | Manufacturing | 2025-10-08 23:31 | tVerifyCAPACompletion | 2025-10-07 15:10 | 2025-11-30 | 2025-11-28 23:00 | 2025-10-07 15:10
CAPA-2023-000285 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | CRB Approval | CLOSED | Naz Shew | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-05 | Manufacturing | 2025-10-08 23:31 | tVerifyCAPAEffectiveness | 2025-10-07 15:14 | 2026-04-05 | 2026-04-03 22:00 | 2025-10-07 15:14
CAPA-2023-000285 | QMS Internal Audit Sonova and Unitron Canada FY2022/2023 | CRB Approval | CLOSED | Naz Shew | Omid Jalili | 2023-04-20 15:13 | 5200 | Audit | 2026-04-05 | Manufacturing | 2025-10-08 23:31 | tCRBApproval | 2025-10-08 14:13 | 2025-10-07 11:14 |  | 2025-10-08 23:31
CAPA-2025-000487 | QMS Internal Audit Sonova/Phonak AG -Inadequate Process Trending in Management Reviews | Completion Review | INWORKS | Aurèle Tenaud | Noelia Barrios | 2025-01-30 13:49 | 1100 | NC | 2026-04-24 | Management Responsibilities |  | tVerifyCAPACompletion |  | 2025-10-06 08:02 |  | 2025-10-06 06:02
CAPA-2025-000487 | QMS Internal Audit Sonova/Phonak AG -Inadequate Process Trending in Management Reviews | Completion Review | INWORKS | Aurèle Tenaud | Noelia Barrios | 2025-01-30 13:49 | 1100 | NC | 2026-04-24 | Management Responsibilities |  | tVerifyCAPACompletion |  | 2026-04-30 | 2026-04-28 22:00 | 2025-10-06 06:02
CAPA-2025-000498 | Sonova/Phonak AG - GMED Audit 2025 NC02 - The last management review planned and carried out in 2025 does not take into consideration customer satisfaction. | Completion Review | INWORKS | Aurèle Tenaud | Omid Jalili | 2025-03-24 08:16 | 1100 | External Audit | 2026-03-24 | Management Responsibilities |  | tVerifyCAPACompletion |  | 2025-10-06 08:04 |  | 2025-10-06 06:06
CAPA-2025-000498 | Sonova/Phonak AG - GMED Audit 2025 NC02 - The last management review planned and carried out in 2025 does not take into consideration customer satisfaction. | Completion Review | INWORKS | Aurèle Tenaud | Omid Jalili | 2025-03-24 08:16 | 1100 | External Audit | 2026-03-24 | Management Responsibilities |  | tVerifyCAPACompletion |  | 2026-01-30 | 2026-03-13 23:00 | 2025-10-06 06:06
CAPA-2025-000534 | Parts released without ISIR | Investigation | INWORKS | Diana Waldmann | Omid Jalili | 2025-09-09 07:36 | 1100 | NC | 2025-12-08 |  |  | tApproveDueDateExtension | 2025-10-23 07:34 | 2025-10-23 09:32 |  | 2025-10-23 07:34
CAPA-2025-000534 | Parts released without ISIR | Investigation | INWORKS | Diana Waldmann | Omid Jalili | 2025-09-09 07:36 | 1100 | NC | 2025-12-08 |  |  | tApproveDueDateExtension | 2025-10-23 07:34 | 2025-10-23 09:32 |  | 2025-10-23 07:34
CAPA-2025-000548 | ITE 60 Day Reliability Rate KPI in the Red for 3 Months | Initiation Verification | INWORKS | Reanne Hamilton | Reanne Hamilton | 2025-10-23 14:28 | 2550 | Other |  | Manufacturing |  | tVerifyCAPAInitiation |  | 2025-10-23 14:28 |  | 2025-10-23 14:29
CAPA-2025-000548 | ITE 60 Day Reliability Rate KPI in the Red for 3 Months | Initiation Verification | INWORKS | Reanne Hamilton | Reanne Hamilton | 2025-10-23 14:28 | 2550 | Other |  | Manufacturing |  | tVerifyCAPAInitiation |  | 2025-10-23 14:28 |  | 2025-10-23 14:29
CAPA-2025-000549 | Freight costs above budget April 2024 - February 2025 | Initiation Verification | INWORKS | Anna Rajtmajer | Reanne Hamilton | 2025-10-23 19:36 | 2550 | Management Review |  | Sales Inventory & Operation planning |  | tVerifyCAPAInitiation |  | 2025-10-23 19:36 |  | 2025-10-23 19:36
CAPA-2025-000549 | Freight costs above budget April 2024 - February 2025 | Initiation Verification | INWORKS | Anna Rajtmajer | Reanne Hamilton | 2025-10-23 19:36 | 2550 | Management Review |  | Sales Inventory & Operation planning |  | tVerifyCAPAInitiation |  | 2025-10-23 19:36 |  | 2025-10-23 19:36
CAPA-2025-000486 | Incomplete documentation and records related to the qualifications of local suppliers | CRB Approval | INWORKS | Omveer Khanchi | Reanne Hamilton | 2025-01-24 16:42 | 2550 | External Audit | 2026-04-01 | Procurement & Supplier Control | 2025-09-29 13:44 |  |  |  |  | 2025-09-29 13:44
CAPA-2025-000486 | Incomplete documentation and records related to the qualifications of local suppliers | CRB Approval | INWORKS | Omveer Khanchi | Reanne Hamilton | 2025-01-24 16:42 | 2550 | External Audit | 2026-04-01 | Procurement & Supplier Control | 2025-09-29 13:44 |  |  |  |  | 2025-09-29 13:44
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-20 11:16 | 2025-11-19 |  | 2025-10-20 13:50
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-20 13:50 | 2025-11-19 |  | 2025-10-20 13:50
CAPA-2024-000453 | QMS Internal Audit Sonova do Brasil FY2023/2024 - Failure in the control and monitoring in the storage temperature conditions in Manufacturing area. | Investigation | INWORKS | Rafael Massola | Fernanda Meisel | 2024-08-26 15:12 | 6300 | Audit | 2024-11-25 | Facility Management |  | tVerifyImplementation | 2025-10-20 11:07 | 2025-10-17 15:09 |  | 2025-10-20 12:35
CAPA-2025-000521 | SCIP database not being updated (REACH) | Implementation | INWORKS | Matthias Etter | Fadime Hosoglu Leahy | 2025-07-07 14:14 | 1100 | NC | 2026-11-19 | Regulatory Affairs |  | tApproveCAPAInvestigation | 2025-10-20 11:20 | 2025-11-19 |  | 2025-10-20 13:50
CAPA-2024-000453 | QMS Internal Audit Sonova do Brasil FY2023/2024 - Failure in the control and monitoring in the storage temperature conditions in Manufacturing area. | Investigation | INWORKS | Rafael Massola | Fernanda Meisel | 2024-08-26 15:12 | 6300 | Audit | 2024-11-25 | Facility Management |  | tInvestigateCAPA |  | 2025-10-20 08:07 |  | 2025-10-20 12:35
CAPA-2024-000453 | QMS Internal Audit Sonova do Brasil FY2023/2024 - Failure in the control and monitoring in the storage temperature conditions in Manufacturing area. | Investigation | INWORKS | Rafael Massola | Fernanda Meisel | 2024-08-26 15:12 | 6300 | Audit | 2024-11-25 | Facility Management |  | tInvestigateCAPA |  | 2024-11-25 |  | 2025-10-20 12:35
CAPA-2024-000354 | Smoking and melted device | Closed | CLOSED | Christian Mueller | CAPACoordinator Murten | 2024-01-10 12:45 | 1300 | Customer Complaint Handling | 2026-04-08 |  | 2025-10-10 09:00 |  |  |  |  | 2025-10-10 09:00
CAPA-2024-000444 | Health Canada Inspection (2024) - Observations #2 and #6 | Implementation | INWORKS | Leo Lau | Omid Jalili | 2024-08-07 02:43 | 5200 | External Audit | 2025-12-19 | Regulatory Affairs |  | tInvestigateCAPA | 2025-06-01 01:43 | 2024-12-19 |  | 2025-06-01 01:43
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | CRB Approval | INWORKS | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs |  | tVerifyCAPACompletion | 2025-10-09 16:16 | 2025-09-30 |  | 2025-10-27 18:31
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | CRB Approval | INWORKS | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs |  | tVerifyCAPACompletion | 2025-10-27 18:31 | 2025-06-30 |  | 2025-10-27 18:31
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | CRB Approval | INWORKS | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs |  | tVerifyCAPAEffectiveness | 2025-10-28 02:13 | 2025-10-27 14:31 |  | 2025-10-28 02:13
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | CRB Approval | INWORKS | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs |  | tVerifyCAPAEffectiveness | 2025-10-28 02:13 | 2026-04-25 | 2026-04-23 22:00 | 2025-10-28 02:13
CAPA-2025-000520 | QMS Internal Audit Sonova USA FY2023/2024 | Investigation Approval | INWORKS | Minal Maurya | Andres Uribe | 2025-06-30 21:22 | 5100 | Audit | 2025-11-12 | Quality- / Environment Management |  | tApproveCAPAInvestigation |  | 2025-11-12 |  | 2025-10-27 21:01
CAPA-2025-000520 | QMS Internal Audit Sonova USA FY2023/2024 | Investigation Approval | INWORKS | Minal Maurya | Andres Uribe | 2025-06-30 21:22 | 5100 | Audit | 2025-11-12 | Quality- / Environment Management |  | tApproveCAPAInvestigation |  | 2025-10-27 15:58 |  | 2025-10-27 21:01
CAPA-2025-000520 | QMS Internal Audit Sonova USA FY2023/2024 | Investigation Approval | INWORKS | Minal Maurya | Andres Uribe | 2025-06-30 21:22 | 5100 | Audit | 2025-11-12 | Quality- / Environment Management |  | tApproveCAPAInvestigation |  | 2025-11-12 |  | 2025-10-27 21:01
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | CRB Approval | INWORKS | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs |  | tCRBApproval |  | 2025-10-27 22:13 |  | 2025-10-28 02:13
CAPA-2024-000443 | Health Canada Inspection (2024) - [Observation #1b] | CRB Approval | INWORKS | Shabeena Ibrahim | Leo Lau | 2024-08-06 18:34 | 5200 | External Audit | 2026-04-25 | Regulatory Affairs |  | tCRBApproval |  | 2025-10-27 22:13 |  | 2025-10-28 02:13
CAPA-2023-000276 | QMS Internal Audit Regional Center South Europe FY2022/2023-Design Transfer | CRB Approval | CLOSED | Omid Jalili | Ana Belen Gil Saez | 2023-04-18 06:46 | 1100 | Audit | 2025-07-13 | Manufacturing | 2025-09-23 13:15 |  |  |  |  | 2025-09-23 13:15
CAPA-2025-000538 | Improvement of Service Process | Investigation | INWORKS | Andrea Huell | Diana Waldmann | 2025-09-23 13:15 | 1100 | Audit | 2025-11-07 | Product Service |  | tVerifyCAPAInitiation | 2025-09-29 13:16 | 2025-09-23 15:15 |  | 2025-09-29 13:16
CAPA-2025-000538 | Improvement of Service Process | Investigation | INWORKS | Andrea Huell | Diana Waldmann | 2025-09-23 13:15 | 1100 | Audit | 2025-11-07 | Product Service |  | tVerifyCAPAInitiation | 2025-09-29 13:16 | 2025-09-23 15:15 |  | 2025-09-29 13:16
CAPA-2025-000501 | Volume of clarifications | Implementation | INWORKS | Mark Critchley | Reanne Hamilton | 2025-05-19 09:38 | 2550 | Other | 2026-10-01 | Order Management & Return |  | tImplementActionPlans |  | 2025-12-19 | 2025-12-17 23:00 | 2025-10-17 14:12
CAPA-2025-000501 | Volume of clarifications | Implementation | INWORKS | Mark Critchley | Reanne Hamilton | 2025-05-19 09:38 | 2550 | Other | 2026-10-01 | Order Management & Return |  | tImplementActionPlans |  | 2025-12-19 | 2025-12-17 23:00 | 2025-10-17 14:12
CAPA-2025-000524 | Incomplete Identification of Nonconforming Packaging in Quarantine Area | Investigation | INWORKS | Loredana Neagu | Reanne Hamilton | 2025-07-15 15:58 | 2550 | External Audit | 2025-11-10 | CAPA/NC |  | tInvestigateCAPA |  | 2025-10-27 11:51 |  | 2025-10-27 11:52
CAPA-2025-000524 | Incomplete Identification of Nonconforming Packaging in Quarantine Area | Investigation | INWORKS | Loredana Neagu | Reanne Hamilton | 2025-07-15 15:58 | 2550 | External Audit | 2025-11-10 | CAPA/NC |  | tInvestigateCAPA |  | 2025-11-10 | 2025-11-08 23:00 | 2025-10-27 11:52
CAPA-2025-000524 | Incomplete Identification of Nonconforming Packaging in Quarantine Area | Investigation | INWORKS | Loredana Neagu | Reanne Hamilton | 2025-07-15 15:58 | 2550 | External Audit | 2025-11-10 | CAPA/NC |  | tApproveCAPAInvestigation | 2025-10-27 11:51 | 2025-10-20 14:49 |  | 2025-10-27 11:52
CAPA-2025-000524 | Incomplete Identification of Nonconforming Packaging in Quarantine Area | Investigation | INWORKS | Loredana Neagu | Reanne Hamilton | 2025-07-15 15:58 | 2550 | External Audit | 2025-11-10 | CAPA/NC |  | tApproveCAPAInvestigation | 2025-10-27 11:51 | 2025-11-10 |  | 2025-10-27 11:51
Total number of records: 12555

## Committed Date
CAPA Number | Committed Date | To be overdue
CAPA-2023-000275 | 2025-10-31 | On Time
CAPA-2023-000346 | 2025-11-30 | To be overdue
CAPA-2023-000312 | 31-Apr-26 | To be overdue
CAPA-2021-000096 | 2025-10-31 | To be overdue